## Project Budget - 1-2019
Construction |  | Changes
General Contract - Transmission Main | 1446000 | estimate | 1446000
General Contract - 2.0 MG Storage Tank & Mixing | 4958000 | estimate | 4958000
Electrical Contract | 50000 | estiamte | 50000
CONSTRUCTION SUB-TOTAL | 6454000 |  | 6454000
Engineering
Design |  | estimate | 1290800
Bidding |  | estimate | 0
Construction Administration |  | estimate | 0
Construction Observation |  | estimate | 0
Additional Services |  | estimate | 0
Post Construction Services |  | estimate | 0
MRB Design and Construction Engineering Contract Sub-Total |  | estimate | 1290800
Engineering Amendment 1 - reimbursement |  |  | 0
Engineering Amendmet 2 |  |  | 0
ENGINEERING SUB-TOTAL |  |  | 1290800
Other Expenses
Bond Counsel |  | est | 30000
Financial Advisor |  | est | 60000
Local Counsel |  | est | 20000
Miscellaneous |  | est | 70000
Other Expenses - Miscellaneous
Land Acquisition and Easements |  | est | 50000
Sludge Hauling/Disposal |  | est | 0
Lab/Office/Safety Equipment |  | est | 0
Electrical Service Fee |  | est | 10000
Special Inspections |  | est | 40000
SCADA Professional Services |  | est | 50000
OTHER EXPENSES SUB-TOTAL |  |  | 330000
PROJECT SUB-TOTAL |  |  | 8074800
Contingency (percent construction) | 14.89% |  | 961200
EFC Issuance Costs (%) |  |  | 0
TOTAL PROJECT COST |  |  | 9036000
BOND RESOLUTION |  |  | 9036000
|  | WIIA Grant | 3614400
|  | Town Contribution | 1000000 | ?
|  | SAM Grant | 0
|  | BALANCE | 4421600

## Project Budget - 4-2019
Construction |  | Changes
General Contract - Transmission Main | 1446000 | estimate | 1446000
General Contract - 2.0 MG Storage Tank & Mixing | 4958000 | estimate | 4958000
Electrical Contract | 50000 | estiamte | 50000
CONSTRUCTION SUB-TOTAL | 6454000 |  | 6454000
Engineering
Preliminary Design |  | estimate | 1290800
Design |  | estimate | 0
Bidding |  | estimate | 0
Construction Administration |  | estimate | 0
Construction Observation |  | estimate | 0
Additional Services |  | estimate | 0
Post Construction Services |  | estimate | 0
MRB Design and Construction Engineering Contract Sub-Total |  | estimate | 1290800
Engineering Amendment 1 - reimbursement |  |  | 0
Engineering Amendmet 2 |  |  | 0
ENGINEERING SUB-TOTAL |  |  | 1290800
Other Expenses
Bond Counsel |  | est | 50000
Financial Advisor |  | est | 75000
Local Counsel |  | est | 20000
Credit Rating? |  | est | 20000
Miscellaneous |  | est | 15000
Other Expenses - Miscellaneous
Land Acquisition and Easements |  | est | 50000
Sludge Hauling/Disposal |  | est | 0
Lab/Office/Safety Equipment |  | est | 0
Electrical Service Fee |  | est | 10000
Special Inspections |  | est | 40000
SCADA Professional Services |  | est | 50000
OTHER EXPENSES SUB-TOTAL |  |  | 330000
PROJECT SUB-TOTAL |  |  | 8074800
Contingency (percent construction) | 14.89% |  | 961200
EFC Issuance Costs (%) |  |  | 0
TOTAL PROJECT COST |  |  | 9036000
BOND RESOLUTION |  |  | 9036000
|  | WIIA Grant | 3614400
|  | Town Contribution | 1000000 | ?
|  | SAM Grant | 0
|  | BALANCE | 4421600

## Project Budget - 6-2019
Construction |  | Changes
General Contract - Transmission Main | 1446000 | estimate | 1446000
General Contract - 2.0 MG Storage Tank & Mixing | 4958000 | estimate | 4958000
Electrical Contract | 50000 | estiamte | 50000
CONSTRUCTION SUB-TOTAL | 6454000 |  | 6454000
Engineering
Preliminary Design |  | estimate | 36000
Design |  | estimate | 348000
Bidding |  | estimate | 35000
Construction Administration |  | estimate | 137000
Construction Observation |  | estimate | 133200
Additional Services |  | estimate | 75000
Post Construction Services |  | estimate | 0
MRB Design and Construction Engineering Contract Sub-Total |  | estimate | 764200
Engineering Amendment 1 - reimbursement |  |  | 0
Engineering Amendmet 2 |  |  | 0
ENGINEERING SUB-TOTAL |  |  | 764200
Other Expenses
Bond Counsel |  | est | 40000
Financial Advisor |  | est | 75000
Local Counsel |  | est | 20000
Credit Rating? |  | est | 20000
Miscellaneous |  | est | 15000
Other Expenses - Miscellaneous
Land Acquisition and Easements |  | est | 50000
Sludge Hauling/Disposal |  | est | 0
Lab/Office/Safety Equipment |  | est | 0
Electrical Service Fee |  | est | 10000
Special Inspections |  | est | 40000
SCADA Professional Services |  | est | 50000
OTHER EXPENSES SUB-TOTAL |  |  | 320000
PROJECT SUB-TOTAL |  |  | 7538200
Contingency (percent construction) | 23.21% |  | 1497800
EFC Issuance Costs (%) |  |  | 0
TOTAL PROJECT COST |  |  | 9036000
BOND RESOLUTION |  |  | 9036000
|  | WIIA Grant | 3614400
|  | Town Contribution | 1000000 | ?
|  | SAM Grant | 0
|  | BALANCE | 4421600

## Project Budget - 6-2019 (2)
Construction |  | Changes
General Contract - Transmission Main | 1446000 | estimate | 1446000
General Contract - 2.0 MG Storage Tank & Mixing | 4958000 | estimate | 4958000
Electrical Contract | 50000 | estiamte | 50000
CONSTRUCTION SUB-TOTAL | 6454000 |  | 6454000
Engineering
Preliminary Design |  | estimate | 36000
Design |  | estimate | 348000
Bidding |  | estimate | 35000
Construction Administration |  | estimate | 137000
Construction Observation |  | estimate | 133200
Additional Services |  | estimate | 75000
Post Construction Services |  | estimate | 0
MRB Design and Construction Engineering Contract Sub-Total |  | estimate | 764200
Engineering Amendment 1 - reimbursement |  |  | 0
Engineering Amendmet 2 |  |  | 0
ENGINEERING SUB-TOTAL |  |  | 764200
Other Expenses
Bond Counsel |  | est | 40000
Financial Advisor |  | est | 75000
Local Counsel |  | est | 20000
Credit Rating? |  | est | 20000
Miscellaneous |  | est | 15000
Other Expenses - Miscellaneous
Land Acquisition and Easements |  | est | 50000
Sludge Hauling/Disposal |  | est | 0
Lab/Office/Safety Equipment |  | est | 0
Electrical Service Fee |  | est | 10000
Special Inspections |  | est | 40000
SCADA Professional Services |  | est | 50000
OTHER EXPENSES SUB-TOTAL |  |  | 320000
PROJECT SUB-TOTAL |  |  | 7538200
Contingency (percent construction) | 14.9% |  | 961800
EFC Issuance Costs (%) |  |  | 0
TOTAL PROJECT COST |  |  | 8500000
BOND RESOLUTION |  |  | 9036000
|  | WIIA Grant | 3614400
|  | Town Contribution | 1000000 | ?
|  | SAM Grant | 0
|  | BALANCE | 3885600

## Project Budget - 12-2020
Construction
General Contract w/ Alternates - Transmission Main | 1446000 | est | 1446000
Tank Contract - 2.0 MG Storage Tank & Mixing | 4958000 | est | 4958000
Electrical Contract | 50000 | est | 50000
HVAC Contract | 0 | est | 0
CONSTRUCTION SUB-TOTAL | 6454000 |  | 6454000
Engineering
Preliminary Design |  |  | 36000
Design |  |  | 348000
Bidding |  |  | 35000
Construction Administration |  |  | 137000
Construction Observation |  |  | 133200
Additional Services |  |  | 75000
MRB Design and Construction Engineering Contract Sub-Total |  |  | 764200
Engineering Amendment 1 - reimbursement (placeholder) |  |  | 10796.5
ENGINEERING SUB-TOTAL |  |  | 774996.5
Other Expenses - Admin
Bond Counsel |  | est | 50000
Financial Advisor |  | est | 75000
Local Counsel |  | est | 20000
Miscellaneous |  | est | 15000
Other Expenses - Miscellaneous
Land Acquisition and Easements |  | est | 50000
Electrical Service Fee |  | est | 10000
Special Inspections |  | est | 40000
SCADA Professional Services |  | est | 50000
Credit Rating Charge |  | est | 20000
OTHER EXPENSES SUB-TOTAL |  |  | 330000
PROJECT SUB-TOTAL |  |  | 7558996.5
Contingency (percent construction) | 14.58% |  | 941003.5
EFC Issuance Costs (%) |  |  | 0
TOTAL PROJECT COST |  |  | 8500000
BOND RESOLUTION |  |  | 9036000
|  | WIIA Grant | 3614400
|  | Town Contribution | 1000000 | ?
|  | BALANCE TO FINANCE | 3885600

## Project Budget - 12-2021
Construction
General Contract w/ Alternates - Transmission Main | 2632592 | Bid Price | 2632592
Tank Contract - 2.0 MG Storage Tank & Mixing | 7932000 | Bid Price | 7932000
Electrical Contract | 332102 | Bid Price | 332102
HVAC Contract | 59250 | Bid Price | 59250
CONSTRUCTION SUB-TOTAL | 10955944 |  | 10955944
Engineering
Preliminary Design |  |  | 36000
Design |  |  | 348000
Bidding |  |  | 35000
Construction Administration |  |  | 137000
Construction Observation |  |  | 133200
Additional Services |  |  | 75000
MRB Design and Construction Engineering Contract Sub-Total |  |  | 764200
Engineering Amendment 1 - reimbursement (placeholder) |  |  | 10796.5
ENGINEERING SUB-TOTAL |  |  | 774996.5
Other Expenses - Admin
Bond Counsel |  | est | 50000
Financial Advisor |  | est | 75000
Local Counsel |  | est | 20000
Miscellaneous |  | est | 15000
Other Expenses - Miscellaneous
Land Acquisition and Easements |  | est | 50000
Electrical Service Fee |  | est | 10000
Special Inspections |  | est | 40000
SCADA Professional Services |  | est | 50000
Credit Rating Charge |  | est | 20000
OTHER EXPENSES SUB-TOTAL |  |  | 330000
PROJECT SUB-TOTAL |  |  | 12060940.5
Contingency (percent construction) | 8.215% |  | 900000
EFC Issuance Costs (%) |  |  | 0
TOTAL PROJECT COST |  |  | 12960940.5
BOND RESOLUTION |  |  | 9036000
UPDATED BOND RESOLUTION |  |  | 13000000
|  | WIIA Grant | 3614400
|  | Town Contribution | 1000000 | ?
|  | BALANCE TO FINANCE | 8346540.5